## Sheet1
S.No | Task Detail | Assignment Date | Start Date | Deadline Date | Status | Responsible Person | Completed Date
1 | Dashboard Home Design | 2021-02-08 | 2021-02-12 | 2021-02-28 | In Queue | Yash Gaur
2 | Login Page Backend API | 2021-02-13 | 2021-02-13 | 2021-02-28 | In Queue | Raghvendra Awasthi
3 | Distributor Profile | 2021-02-13 | 2021-02-15 | 2021-02-28 | In Queue | Yash Gaur
4 | Product Master
| Categories (Create, View, Update, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 | 2021-02-17 | 2021-02-28 | In Queue | Both
| Sub Categories (Create, View, Update, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 | 2021-02-18 | 2021-02-28 | In Queue | Both
| Product (Create, View, Update, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 |  | 2021-02-28 |  | Both
| Pkt/Bag (Create, View, Active-Deactive, Export(Clipboard Copy, PDF, Excel, Print)) | 2021-02-17 |  | 2021-02-28 |  | Both
| Add Payout | 2021-02-17 |  | 2021-02-28 |  | Both
| Waste/Damage Stock | 2021-02-17 |  | 2021-02-28 |  | Both